## Sheet1
Task | Expected Date of Completion | Actual Date of completion | Reasoning
Topic Proposal | Feb-5-2021 | Feb-5-2021 | N/A
Requirment Specification | Mar-31-2021 | Mar-31-2021 | N/A
Use Cases | Mar-31-2021 | Mar-31-2021 | N/A
SPMP | Mar-31-2021 | Mar-31-2021 | N/A
Proposed Design | Mar-31-2021 | Mar-31-2021 | N/A
Design Review Mtg | Mar-31-2021 | Apr- 09-2021 | The Apointment Calander was booked until April
Tool Selection Review Mtg | Mar-31-2021 | Apr- 09-2021 | The Apointment Calander was booked until April
System Test Procedure (Individual Project) | Apr-24-2021 | Apr-26-2021 | had a family emergeny and it affected my ability to complete the task on time.